## Bug Report
Bug Report
Category | Label | Value
Bug ID | ID Number | BR001
| Name | Last Name input field is unresponsive
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | The "Last Name" field does not accept keyboard input or data entry.
| URL | https://www.saucedemo.com/checkout-step-one.html
| Screenshot | https://drive.google.com/file/d/1pzZWhYXMwgxye7T7v3RwD2iUVCEIT8Gs/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Add item to cart. 3. Go to Checkout. 4. Try typing in Last Name.
| Expected Results | Field should accept and display the entered text.
| Actual Results | Field is frozen and ignores all keyboard inputs.
| Priority | High
Notes
Category | Label | Value
Bug ID | ID Number | BR002
| Name | Invalid mathematical expression in Product Price
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | "Sauce Labs Fleece Jacket" displays a mathematical error instead of a price.
| URL | https://www.saucedemo.com/inventory-item.html?id=6
| Screenshot | https://drive.google.com/file/d/1T6mSQCXCrUrPck4w77onAd6Fuag3Mf25/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | Login as problem_user. 2. Click on "Sauce Labs Fleece Jacket". 3. Observe the price.
| Expected Results | Price should be displayed as a normal currency value (e.g. $49.99).
| Actual Results | Price shows an invalid math symbol (Square root of negative number).
| Priority | High
Notes
Category | Label | Value
Bug ID | ID Number | BR003
| Name | Product Sorting/Filtering dropdown is unresponsive
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | Sorting products (Price, A-Z) does not change the item order on the page.
| URL | https://www.saucedemo.com/inventory.html
| Screenshot | https://drive.google.com/file/d/1OLvRtRtc5Svhlllxclg4Y-cU4gDNuYIv/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Click Sort dropdown. 3. Select "Price (low to high)".
| Expected Results | Products should re-order based on price.
| Actual Results | Product order remains static regardless of the selected filter.
| Priority | Medium
Notes
Category | Label | Value
Bug ID | ID Number | BR004
| Name | All product images are broken or incorrect
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | Global image mismatch; all items show a placeholder/incorrect dog image.
| URL | https://www.saucedemo.com/inventory.html
| Screenshot | https://drive.google.com/file/d/1b0y2_nVsiaQIa55HrWSzyeexliYoyBQ3/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Check the inventory list images.
| Expected Results | Each product should show its specific, correct image.
| Actual Results | Every product displays the same incorrect image/broken link.
| Priority | Low
Notes
Category | Label | Value
Bug ID | ID Number | BR005
| Name | Product link redirects to the wrong details page
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | Clicking a product title opens a details page for a completely different item.
| URL | https://www.saucedemo.com/inventory.html
| Screenshot | https://drive.google.com/file/d/1iaBZEjEZ9gqSKXK8T5mm1f2hrvUF4GTK/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Click on "Sauce Labs Backpack".
| Expected Results | Redirect to Backpack details page.
| Actual Results | Redirects to Fleece Jacket or another product detail page.
| Priority | High
Notes
Category | Label | Value
Bug ID | ID Number | BR006
| Name | "Remove" button fails to function for Backpack
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | The "Remove" button is unresponsive on the inventory page after adding the Backpack, preventing item removal.
| URL | https://www.saucedemo.com/inventory.html
| Screenshot | https://drive.google.com/file/d/1V0ckz9E6Xtrbl6tXB6UBf675GBimW92P/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Add Backpack to cart. 3. Click "Remove".
| Expected Results | Item should be removed and badge count decreased.
| Actual Results | Button is clicked but item remains in cart.
| Priority | Medium
Notes
Category | Label | Value
Bug ID | ID Number | BR007
| Name | Unable to add "Bolt T-Shirt" to shopping cart
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | The "Add to Cart" button for the Bolt T-Shirt does not register any action, making it impossible to buy.
| URL | https://www.saucedemo.com/inventory.html
| Screenshot | https://drive.google.com/file/d/1WQToy1VRZjlAg-zu9BjsW6ml4uG-FD07/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Click "Add to cart" for Bolt T-Shirt.
| Expected Results | Button text changes to "Remove" and cart count increases.
| Actual Results | Button does not respond to clicks.
| Priority | Medium
Notes
Category | Label | Value
Bug ID | ID Number | BR008
| Name | "Add to cart" button broken for Fleece Jacket
| Reporter | Motasem Douli
| Submit Date | 2025-11-01
Bug Overview | Summary | The "Add to Cart" function is completely disabled for the Fleece Jacket product for this user account.
| URL | https://www.saucedemo.com/inventory.html
| Screenshot | https://drive.google.com/file/d/1_EMudSvKE8cy5GNwdf759t2_rTTxpJAX/view?usp=drive_link
Environment | Platform | PC
| Operating System | Windows 11 Pro
| Browser | Microsoft Edge
Bug Details | Steps to Reproduce | 1. Login as problem_user. 2. Click "Add to cart" for Fleece Jacket.
| Expected Results | System adds the item to the cart immediately.
| Actual Results | No action triggered upon clicking the button.
| Priority | Medium
Notes